COURSE: AGILE PROJECT MANAGEMENT

MR KUATE

EXPENSE TRACKER Product Backlog, Sprint Plan & Acceptance Criteria

SCRUM TEAM

Biloa Ekassi Lena

Tagne Fadhil

Djou Ningaye Simon

Nguma Kelimbom

Yuhnekeh Sidney Brown

Academic Year 2026 to 2027

# Revision Note

This document replaces the Product Backlog and Sprint sections of our earlier submission. It keeps the project as it was defined in the Product Vision document and in the team's role assignments; nothing about the product itself has changed. What changes is how the backlog is organized.

After the first presentation came back from the review: the backlog did not read as a clear build order from project start to final product, and our user stories did not carry acceptance criteria. Both are addressed directly below: the backlog is now ordered and grouped by sprint with explicit dependencies (Section 5), and the stories that matter most for an early sprint each carry Given/When/Then criteria (Section 6). Stories further down the roadmap will get the same treatment during backlog refinement, ahead of their own sprint, rather than all at once up front: that is closer to how the team will actually use this document during the project.

Everything else: the product vision, the financial rules, the team's Scrum roles: is carried over from the existing Product Vision and Team Roles documents and is only summarized here for context.

# 1. Project Context

Expense Tracker is a mobile personal finance application built with React Native on the client and Spring Boot on the backend. Each user has a single private account on their own device; income and expenses are tracked from the moment the account is created, and budgeting sits on top of that as something the user can turn on whenever they want rather than something they have to set up first.

The financial logic follows one cycle: TRACK, then optionally PLAN, then MONITOR, then UNDERSTAND. A user records income and expenses with no setup barrier. They can, whenever they choose, set a budget goal for a financial period of their own length (minimum one week) and split it across categories. The application compares actual spending to that goal without ever blocking a transaction, and separately calculates savings or debt directly from income minus actual expenses, whether or not a budget exists. Outstanding debt carries into the next period and is deducted from the following period's income.

The team is five students working roughly four months in two week sprints. Sprint 0 is a setup sprint with no user facing story; Sprints 1 through 7 deliver the product feature by feature; Sprint 8 is hardening and release. Nine sprints of two weeks is about eighteen weeks, which lines up with the four month window agreed with the Product Owner; if the academic calendar ends up tighter than that, the sprints most likely to be trimmed are Sprint 7 (AI Assistant) since it depends on everything before it and adds the least to the core product.

# 2. Scrum Team & Responsibilities

All five members act as developers; two also carry the Product Owner and Scrum Master roles on top of that.

| Name | Role | Responsibility |
| --- | --- | --- |
| Yuhnekeh Sidney Brown | Product Owner (also Developer) | Owns the backlog and its order; writes and clarifies user stories and acceptance criteria; accepts or rejects work at the end of each sprint; keeps the team anchored to the idea that tracking never depends on budgeting. |
| Tagne Fadhil | Scrum Master (also Developer) | Runs Sprint Planning, the Daily Stand up, Sprint Review and Retrospective; removes blockers; keeps the Definition of Done honest. |
| Biloa Ekassi Lena | Developer | Implementation and testing for assigned stories each sprint. |
| Nguma Kelimbom | Developer | Implementation and testing for assigned stories each sprint. |
| Djou Ningaye Simon | Developer | Implementation and testing for assigned stories each sprint. |

### Daily Stand up

Each working day, in fifteen minutes or less, every developer answers three questions: what did I finish yesterday that helped the Sprint Goal, what will I work on today, and is anything blocking me or the team.

# 3. Product Scope by Epic

The backlog groups naturally into ten functional areas. These are organizing labels, not a build order on their own: Section 5 turns them into one.

| Epic | Purpose |
| --- | --- |
| User & Account Management | Secure personal accounts |
| Income Management | Record and calculate income |
| Expense & Category Management | Manual and automatic expense recording, fully standalone from budgeting |
| Budgeting & Financial Planning | Optional flexible length budget goals and category allocations |
| Monitoring, Savings & Debt | Calculate financial performance |
| Dashboard, Reports & Visualization | Help users understand their financial activity |
| Notifications & Alerts | Proactively inform users of budget and debt events |
| AI Financial Assistant | Guidance and conversational financial support |
| Administration & Platform Management | Operate the platform without access to user financial data |
| Future Engagement Features | Mascot and other optional engagement ideas, deferred |

# 4. How the Backlog Is Ordered

The backlog below is ordered the way the product actually has to be built, not alphabetically and not by epic name. Each story lists what it depends on, so the sequence is something a reader can check rather than take on faith.

- Account and session come first, since every other feature belongs to an authenticated user.

- Income and expense tracking come next, and specifically before budgeting: the product's own rule is that tracking never requires a budget to exist first.

- Budgeting comes after tracking works, because a budget is compared against real income and expense records that already need to exist.

- Automatic capture (receipt and mobile money) comes after manual expense recording, since captured data still becomes an ordinary expense record once confirmed.

- Monitoring, savings and debt come after both tracking and budgeting, since they are calculated from that data.

- Dashboard, reports and notifications come after the calculations they display or react to exist.

- The AI assistant comes last among feature sprints, since it reads and acts on data produced by every earlier feature.

Priority is separate from sequence: a P1 story can still come before a P0 story if the P0 story depends on it. The four levels used are:

| Level | Covers |
| --- | --- |
| P0: Critical | Account creation and login; income; standalone expense and category tracking (manual, receipt, mobile money); expense monitoring; core dashboard. |
| P1: High | Profile management; password recovery; expense history/filter/search; optional budgeting; savings and debt calculation; reports. |
| P2: Medium | Notifications; period comparisons; AI assistant; administration. |
| P3: Future | Mascot and other engagement features. |

# 5. Product Backlog

Every story follows the standard As a / I want / so that structure. The order below is the reading order of the whole backlog, grouped by epic and by the sprint each group lands in: this is the chronology the previous submission was missing.

| # | ID | User Story | Pri. | Depends On |
| --- | --- | --- | --- | --- |
| E1: Account & Session: Sprint 1 |  |  |  |  |
| 1 | US01 | As a new user, I want to create a personal account with my required information so that I can securely manage my financial information. | P0 | None |
| 2 | US02 | As a registered user, I want to log in with my credentials so that I can access my financial information. | P0 | US01 |
| 3 | US03 | As a user, I want to log out so that my financial information is protected once I stop using the application. | P0 | US02 |
| 4 | US04 | As a user, I want my session to be securely managed so that unauthorized people cannot access my financial information. | P0 | US02 |
| 5 | US05 | As a user, I want to view and edit my profile information so that my account details stay accurate. | P1 | US01 |
| 6 | US06 | As a user, I want to reset my password when I forget it so that I can regain access to my account. | P1 | US01 |
| E9: Administration & Platform Management: Sprint 1 |  |  |  |  |
| 7 | US07 | As an administrator, I want to authenticate through a separate admin login so that only authorized staff can manage the platform. | P2 | US01 |
| 8 | US08 | As an administrator, I want to manage user account status so that I can keep the platform secure without touching anyone's financial data. | P2 | US07 |
| 9 | US09 | As an administrator, I want to manage the platform's default expense categories so that new users start with a sensible category structure. | P2 | US07 |
| 10 | US10 | As an administrator, I want to monitor technical platform health and errors so that I can spot problems early. | P2 | US07 |
| 11 | US11 | As an administrator, I must be technically prevented from accessing a user's income, expenses, budgets, savings, debt or reports, so that user privacy is respected even at the platform level. | P0 | US07 |
| E2: Income Management: Sprint 2 |  |  |  |  |
| 12 | US12 | As a user, I want to add an income record with its amount, source and date so that my income is accurately recorded. | P0 | US02 |
| 13 | US13 | As a user, I want to view my income records so that I can see the money I have received. | P0 | US12 |
| 14 | US14 | As a user, I want to edit an income record so that incorrect information does not affect my financial calculations. | P1 | US12 |
| 15 | US15 | As a user, I want to delete an incorrectly recorded income entry so that my financial information stays accurate. | P1 | US12 |
| 16 | US16 | As a user, I want the application to calculate my total income for a financial period so that I know how much money I received. | P0 | US12 |
| E3: Expense & Category Management (standalone tracking): Sprint 2 |  |  |  |  |
| 17 | US17 | As a user, I want to create an expense category so that I can organize my spending, without needing a budget first. | P0 | US02 |
| 18 | US18 | As a user, I want to edit a category so that my expense organization stays accurate. | P1 | US17 |
| 19 | US19 | As a user, I want to delete an unused category so that my financial information stays organized. | P1 | US17 |
| 20 | US20 | As a user, I want to record an expense with its amount, category, date and description so that my actual spending is tracked, whether or not I have a budget. | P0 | US17 |
| 21 | US21 | As a user, I want to view my expense history so that I can monitor previous spending. | P0 | US20 |
| 22 | US22 | As a user, I want to view the details of an expense so that I can verify a transaction. | P1 | US21 |
| 23 | US23 | As a user, I want to edit an expense so that I can correct inaccurate information. | P1 | US20 |
| 24 | US24 | As a user, I want to delete an incorrectly recorded expense so that it does not affect my financial calculations. | P1 | US20 |
| 25 | US25 | As a user, I want to filter expenses by category and date so that I can find relevant transactions quickly. | P1 | US21 |
| 26 | US26 | As a user, I want to search my expenses so that I can quickly locate a specific transaction. | P1 | US21 |
| E4: Budgeting & Financial Planning (optional layer): Sprint 3 |  |  |  |  |
| 27 | US27 | As a user, I want to choose the length of my financial period, with a minimum of one week, so that my spending plan matches my own rhythm. | P1 | US02 |
| 28 | US28 | As a user, I want to optionally create an overall spending budget goal so that I can set a spending plan without it affecting my ongoing tracking. | P1 | US27 |
| 29 | US29 | As a user, I want to assign part of my overall budget to a category so that I can plan spending at category level. | P1 | US28, US17 |
| 30 | US30 | As a user, I want to see my overall budget and category allocations so that I understand how my spending plan is distributed. | P1 | US28, US29 |
| 31 | US31 | As a user, I want the application to check my category allocations against my overall budget before validation so that I can correct inconsistent allocations. | P1 | US29 |
| 32 | US32 | As a user, I want to edit my validated budget within the first 6% of my financial period, up to a limited number of times, so that I can correct early mistakes without resetting my goal indefinitely. | P1 | US31 |
| 33 | US33 | As a user, I want my budget to become fixed once the edit window closes or I reach the edit limit, so that my financial goal keeps its meaning. | P1 | US32 |
| E3 (cont.): Automatic Expense Capture: Sprint 4 |  |  |  |  |
| 34 | US34 | As a user, I want to capture a receipt so that the application can extract expense information without full manual entry. | P0 | US20 |
| 35 | US35 | As a user, I want to review extracted receipt information before confirming it so that incorrect data does not enter my records. | P0 | US34 |
| 36 | US36 | As a user, I want supported mobile money transactions to be detected, either pasted or read directly from my device's messages, so that eligible expenses can be captured without manual entry. | P0 | US20 |
| 37 | US37 | As a user, I want to review and confirm an automatically detected transaction before it becomes a confirmed expense. | P0 | US36 |
| 38 | US38 | As a user, I want the system to flag potential duplicate automatically captured expenses so that the same transaction is not counted twice. | P1 | US34, US36 |
| E5: Monitoring, Savings & Debt: Sprint 5 |  |  |  |  |
| 39 | US39 | As a user, I want to see my total actual expenses for a financial period so that I know how much I have spent. | P0 | US20 |
| 40 | US40 | As a user, I want to see how much I spent in each category so that I understand where my money goes. | P0 | US20, US17 |
| 41 | US41 | As a user, I want to see the difference between my overall budget and my actual expenses, if I have set a budget, so that I know whether I am meeting my goal. | P1 | US28, US39 |
| 42 | US42 | As a user, I want to see the remaining or negative balance for each category so that I can monitor category level spending. | P1 | US29, US40 |
| 43 | US43 | As a user, I want the application to show when actual spending goes past a category budget so that I am aware, without it blocking my spending. | P0 | US42 |
| 44 | US44 | As a user, I want the application to calculate my savings as total income minus actual expenses so that I know how much I retained, whether or not I have a budget. | P1 | US16, US39 |
| 45 | US45 | As a user, I want to view my savings from previous periods so that I can track my progress. | P1 | US44 |
| 46 | US46 | As a user, I want the application to identify when my expenses exceed my income so that I know I have incurred debt. | P1 | US16, US39 |
| 47 | US47 | As a user, I want to view my outstanding debt so that I know what needs to be recovered. | P1 | US46 |
| 48 | US48 | As a user, I want outstanding debt to be carried into my next financial period so that my financial obligations are not lost. | P1 | US46 |
| 49 | US49 | As a user, I want previous debt to be deducted from my next period's income so that the debt is recovered automatically. | P1 | US48 |
| E6: Dashboard, Reports & Visualization: Sprint 6 |  |  |  |  |
| 50 | US50 | As a user, I want a dashboard showing income, expenses, savings, debt and any active budget status so that I understand my situation at a glance. | P0 | US39, US44, US46 |
| 51 | US51 | As a user, I want to view my financial information by day, week, month, year or custom range so that I can analyze the period that interests me. | P1 | US50 |
| 52 | US52 | As a user, I want to visualize spending by category so that I can identify where most of my money goes. | P1 | US40 |
| 53 | US53 | As a user, I want to visualize spending over time so that I can identify changes in my behavior. | P1 | US39 |
| 54 | US54 | As a user, I want to compare financial information between periods so that I can tell whether my spending and savings are improving. | P1 | US51 |
| 55 | US55 | As a user, I want to generate a financial report for a selected period so that I can review my complete activity. | P1 | US50, US51 |
| E7: Notifications & Alerts: Sprint 6 |  |  |  |  |
| 56 | US56 | As a user with an active budget, I want a warning when my spending approaches my goal so that I can adjust if I choose to. | P2 | US41 |
| 57 | US57 | As a user, I want to be informed when I miss my overall or category budget goal so that I am aware. | P2 | US43 |
| 58 | US58 | As a user, I want to be informed when my expenses exceed my income so that I know I have incurred debt. | P2 | US46 |
| 59 | US59 | As a user, I want a reminder before my budget's edit window closes so that I get a final chance to make corrections. | P2 | US32 |
| E8: AI Financial Assistant: Sprint 7 |  |  |  |  |
| 60 | US60 | As a user, I want the AI to analyze my financial activity and suggest ways to save money so that I can improve my financial situation. | P2 | US44, US50 |
| 61 | US61 | As a user, I want to ask questions about my spending in natural language so that I can quickly get financial information. | P2 | US50 |
| 62 | US62 | As a user, I want to ask the AI to compare different periods so that I can understand changes in spending, savings or debt. | P2 | US54 |
| 63 | US63 | As a user with an active budget, I want the AI to analyze my spending rate and predict whether I am likely to miss my goal, so that I can act early. | P2 | US41, US60 |
| 64 | US64 | As a user, I want to add, edit or delete an expense through the AI assistant, with confirmation before any change, so that I can manage my records conversationally. | P2 | US20, US23, US24, US61 |
| E10: Future Engagement (Icebox): Future |  |  |  |  |
| 65 | US65 | As a user, I want a mascot that reacts to my financial progress so that the application feels more engaging. | P3 | None |
| 66 | US66 | As a user, I want the mascot to celebrate financial milestones so that I feel encouraged to keep improving. | P3 | US65 |
| 67 | US67 | As a user, I want to customize the mascot so that the experience feels more personal. | P3 | US65 |

# 6. Acceptance Criteria

Given/When/Then criteria are provided below for the stories that carry the most weight in each sprint: mainly the P0 items and the stories that fix a specific business rule (the budget edit window, the standalone tracking rule, the debt carry forward). The remaining stories will get the same treatment during refinement for their sprint, following the Definition of Ready in Section 7, so that criteria are written close to when they are needed rather than all guessed at once, months in advance.

### US01: Create account

1. Given the user is not yet registered, when they submit valid required information, then an account is created and they can proceed to log in.

2. Given a required field is missing, when the form is submitted, then the account is not created and the missing fields are shown.

3. Given an account already exists with the same identifier (e.g. email/phone), when registration is attempted again, then the system rejects the duplicate.

### US02: Log in

1. Given a registered user enters valid credentials, when they submit the login form, then they are authenticated and reach their own data only.

2. Given invalid credentials are entered, when login is submitted, then access is denied and no session is created.

### US04: Secure session

1. Given a user is authenticated, when the session token expires or is invalidated, then the user is required to log in again before accessing financial data.

2. Given a user logs out, when they try to reuse the previous session, then access is refused.

### US07: Admin authentication

1. Given a staff member holds an administrator account, when they log in through the admin entry point, then they reach the admin area and not a regular user's financial screens.

2. Given a regular user account, when it attempts to reach the admin area, then access is refused.

### US11: Protect financial privacy

1. Given an administrator is authenticated, when they browse the admin area, then no endpoint or screen exposes another user's income, expenses, budget, savings, debt or reports.

2. Given an administrator attempts to query a user's financial data directly (e.g. via an API call), then the request is rejected at the access control layer, not just hidden in the interface.

### US12: Add income

1. Given an authenticated user, when they submit a valid amount, source and date, then the income record is saved and linked to their account.

2. Given a required value is missing or invalid, when the form is submitted, then the record is not saved and the user sees what needs correcting.

3. Given the income is saved, then it is included in the user's total income for that financial period.

### US16: Calculate total income

1. Given one or more income records exist for a financial period, then total income equals the sum of those records.

2. Given an income record is edited or deleted, then total income recalculates automatically without a page refresh being required for correctness.

### US17: Create category

1. Given an authenticated user, when they submit a valid category name, then the category is created and available when recording expenses.

2. Given no budget exists yet, when the user creates a category, then creation still succeeds. Categories never depend on a budget existing.

### US20: Record expense manually

1. Given an authenticated user, when they submit a valid amount, category, date and description, then the expense is saved and appears in the history.

2. Given no budget exists, when the user records an expense, then the expense is still saved normally.

3. Given a budget exists and the new expense causes overspending, when the user submits it, then the expense is still saved; the system never blocks recording because of budget status.

4. Given the amount is missing or not a valid positive number, when the form is submitted, then the expense is rejected with a clear message.

### US21: View expense history

1. Given the user has recorded expenses, when they open the history screen, then expenses are listed with amount, category, date and description, most recent first.

2. Given no expenses have been recorded yet, then the screen shows an empty state rather than an error.

### US25: Filter expenses

1. Given expenses exist, when the user picks a category filter, then only expenses in that category are shown.

2. Given the user also picks a date range, then both the category and date conditions apply together.

3. Given no expense matches the filters, then the screen shows a clear empty result rather than a blank or broken state.

### US27: Define financial period

1. Given a user sets a financial period length, when they enter a value of one week or more, then it is accepted and used for their budget and savings/debt calculations.

2. Given a user enters a period shorter than one week, when they submit it, then it is rejected with an explanation of the one week minimum.

### US28: Create overall budget

1. Given a user chooses to create a budget, when they submit a valid amount for their chosen financial period, then the budget is created in an unvalidated state.

2. Given the user has not created a budget, then income and expense tracking continue to work exactly as before, unaffected.

### US31: Validate budget

1. Given category allocations sum to less than or equal to the overall budget, when the user validates it, then the budget becomes validated and active.

2. Given category allocations exceed the overall budget, when the user attempts to validate, then validation is refused and the user is shown by how much they are over, e.g. "Your category budgets exceed your overall budget by 20 000 FCFA."

3. Given the allocation is corrected, when the user retries validation, then it can succeed.

### US32: Edit budget within window

1. Given a validated budget is still within the first 6% of its financial period and the edit count is below the agreed cap (3 to 4 edits), when the user edits the overall budget or an allocation, then the edit is accepted and the edit count increases by one.

2. Given the 6% window has closed, when the user attempts an edit, then it is refused.

3. Given the edit cap has already been reached, when the user attempts another edit, then it is refused even if time remains in the window.

### US33: Budget locks after window or edit cap

1. Given either the 6% window closes or the edit cap is reached, whichever happens first, then the budget becomes fixed for the rest of that financial period.

2. Given the budget is locked, then it remains visible in historical reports and does not block any further income or expense recording.

### US34: Capture receipt

1. Given the user photographs or uploads a supported receipt image, when capture runs, then the system extracts an amount, a date and, where legible, a merchant or description, for the user to review.

2. Given the extracted data is incomplete or unreadable, when review opens, then the affected fields are left blank for manual entry rather than guessed.

### US35: Review receipt information

1. Given extracted receipt data is shown for review, when the user confirms it, then an expense record is created from that data.

2. Given the user edits a field before confirming, then the corrected value is what gets saved, not the originally extracted one.

3. Given the user has not yet confirmed, then no expense record exists yet from that capture.

### US38: Detect duplicate transactions

1. Given two automatically captured transactions share the same amount, a close timestamp and a similar source, when the second one is processed, then the user is warned it may be a duplicate before it is confirmed.

2. Given the user confirms it is not a duplicate, then both transactions are kept as separate expenses.

### US39: Calculate total expenses

1. Given one or more expenses exist for a financial period, then total actual expenses equals the sum of those expenses for that period.

### US43: Detect category overspending

1. Given a category has an allocated budget and actual spending in that category exceeds it, then the category balance is shown as negative and flagged as overspent.

2. Given the category is overspent, when the user records another expense in it, then the expense is still recorded normally.

### US44: Calculate savings

1. Given total income and total actual expenses for a period, savings is calculated as total income minus total actual expenses.

2. Given no budget exists, then savings is still calculated, since it depends only on income and expenses.

3. Given expenses exceed income, then the result is treated as debt rather than shown as negative savings (see US46).

### US46: Detect debt

1. Given total actual expenses exceed total income for a period, then the system records the difference as debt.

2. Given income exactly equals expenses, then the period shows neither savings nor debt.

### US48: Carry debt forward

1. Given a user ends a financial period with outstanding debt, when the next financial period starts, then that debt amount is attached to the new period.

2. Given the debt has been deducted once from a later period's income (US49), then it is not deducted again.

### US50: View financial dashboard

1. Given the user has at least one income or expense record, when they open the dashboard, then it shows income, actual expenses, and savings or debt for the current period.

2. Given the user has an active budget, then the dashboard also shows budget status; given they do not, that section is simply omitted rather than shown as broken or zeroed out.

### US56: Budget goal warning

1. Given an active budget and actual spending reaches an agreed threshold of the goal (to be set by the team, e.g. 80%), when that threshold is crossed, then the user receives a warning notification.

2. Given spending is still below the threshold, then no warning is sent.

### US64: Manage expenses through chat

1. Given the user asks the assistant to add, edit or delete an expense, when the assistant proposes the change, then nothing is modified until the user explicitly confirms it.

2. Given the user confirms, then the underlying expense record is updated and all dependent calculations (totals, budget balance, savings/debt) reflect the change.

3. Given the user declines or ignores the proposal, then no change is applied.

# 7. Definition of Ready & Definition of Done

## Definition of Ready

A story is ready to enter Sprint Planning when:

- it has a clear user and a clear value, in the standard As a / I want / so that form;

- Given/When/Then acceptance criteria are written and agreed with the Product Owner;

- its dependencies are identified and either already done or in the same sprint;

- it is small enough to realistically finish inside one sprint;

- any open question about the story has been resolved with the Product Owner.

## Definition of Done

A story is done when:

- the functionality is implemented and matches the story;

- all of its acceptance criteria pass;

- input validation and error handling are in place where the story calls for them;

- relevant unit, integration or acceptance tests pass;

- the code has been reviewed by at least one other developer and merged;

- no known critical defect blocks normal use of the feature;

- the Product Owner has accepted the result against the acceptance criteria.

The exact branch, review and merge workflow is being finalized by the developers and the Scrum Master and will be recorded once settled, rather than assumed here.

# 8. Sprint Roadmap

Nine sprints of two weeks, Sprint 0 through Sprint 8. Each sprint below lists its goal, the technical or setup work behind the scenes, the user stories it carries (in backlog order), and the increment it produces: what a reviewer could actually see working at the end of it.

## Sprint 0: Setup & Architecture

Weeks 1 to 2

Goal: Put the technical foundation in place before any feature work starts. This sprint does not deliver a user facing story; the increment is a working skeleton the team can build on.

### Work behind the scenes

- Finalize the application architecture and database schema

- Set up the GitHub repository, branching strategy and GitHub Projects board

- Set up the Jenkins CI/CD pipeline on the team's VPS, connected through GitHub webhooks

- Agree the Definition of Ready and Definition of Done as a team

- Scaffold the React Native app and the Spring Boot backend, connected to PostgreSQL

- Settle the logo and general color theme of the application

### Increment

A working technical skeleton: repository, CI/CD pipeline, empty but connected mobile app and backend, and agreed team conventions.

## Sprint 1: Account, Session & Admin Foundation

Weeks 3 to 4

Goal: A user can create an account and securely access the application; the platform can be administered separately from user accounts.

### Work behind the scenes

- Authentication API and password hashing

- Session handling and token expiry

- Admin role separation at the API layer, not just in the UI

### User stories in this sprint

US01, US02, US03, US04, US05, US06, US07, US08, US09, US10, US11

### Increment

A user can register, log in, log out, manage their profile and recover a forgotten password. An administrator can log in separately, manage account status and default categories, and cannot reach any user's financial data.

## Sprint 2: Standalone Expense & Income Tracking

Weeks 5 to 6

Goal: A user can track income and expenses from day one, with no budget required first.

### Work behind the scenes

- Default categories pre seeded on account creation

- Expense/income CRUD endpoints and screens

- Search and filter queries

### User stories in this sprint

US12, US13, US14, US15, US16, US17, US18, US19, US20, US21, US22, US23, US24, US25, US26

### Increment

A user can record income, create categories, record expenses manually, and browse, edit, filter and search their history: the core usable product.

## Sprint 3: Budgeting as an Optional Goal Layer

Weeks 7 to 8

Goal: A user can optionally set a budget goal on top of the tracking that already works.

### Work behind the scenes

- Financial period model

- Allocation vs overall budget validation logic

- 6% window and edit cap enforcement

### User stories in this sprint

US27, US28, US29, US30, US31, US32, US33

### Increment

A user can define a financial period, set an overall budget, allocate it to categories, validate it, and edit it within the agreed window before it locks.

## Sprint 4: Automatic Capture

Weeks 9 to 10

Goal: A user can log an expense without typing it in by hand.

### Work behind the scenes

- Receipt OCR integration and review flow

- Mobile money SMS parsing (paste and direct read) and review flow

- Duplicate detection heuristics

### User stories in this sprint

US34, US35, US36, US37, US38

### Increment

A user can capture a receipt photo or a mobile money message and confirm the extracted data into a real expense. This sprint combines two separate technical problems (image OCR and text parsing), so it carries more schedule risk than the others and should be watched closely at the mid sprint check in.

## Sprint 5: Monitoring, Savings & Debt

Weeks 11 to 12

Goal: A user can see how their spending compares to their plan, and whether they are saving or falling into debt.

### Work behind the scenes

- Aggregation queries for totals and per category spending

- Savings/debt calculation service

- Debt carry forward across periods

### User stories in this sprint

US39, US40, US41, US42, US43, US44, US45, US46, US47, US48, US49

### Increment

A user can see total and category spending, budget balances (if a budget exists), savings or debt for the period, and debt correctly carried into the next one.

## Sprint 6: Dashboard, Reports & Notifications

Weeks 13 to 14

Goal: A user can understand their finances at a glance and get proactively notified about what matters.

### Work behind the scenes

- Dashboard aggregation endpoint

- Chart rendering on the mobile client

- Push notification infrastructure

### User stories in this sprint

US50, US51, US52, US53, US54, US55, US56, US57, US58, US59

### Increment

A user opens the app to a dashboard with income, expenses, savings/debt and budget status, can view trends and generate a report, and receives alerts for budget and debt events.

## Sprint 7: AI Assistant

Weeks 15 to 16

Goal: A user can get financial insight and perform simple actions conversationally.

### Work behind the scenes

- Integration with the chosen AI provider

- Prompt design grounded in the user's own data

- Confirmation step before any write action

### User stories in this sprint

US60, US61, US62, US63, US64

### Increment

A user can ask the assistant about their spending, get savings suggestions, compare periods, get an early warning on budget risk, and add or edit an expense conversationally, always with a confirmation step.

## Sprint 8: Quality, Security & Release

Weeks 17 to 18

Goal: Deliver a stable, tested and demonstrable product.

### Work behind the scenes

- Full regression pass across all sprints, building on tests written incrementally since Sprint 0

- Security review of authentication, session handling and the admin/user data boundary

- Performance check on report generation and expense history for larger datasets

- Backup and recovery check

- Final documentation and the sprint review demo

### Increment

No new features. The increment is a stabilized, demoed build ready for submission.

# 9. Traceability

Every story in the backlog traces the same path: requirement, epic, user story, acceptance criteria, sprint, implementation, test, accepted increment. One worked example, followed all the way through:

| Requirement | Users need to know whether they are saving money or falling into debt. |
| --- | --- |
| Epic | E5: Monitoring, Savings & Debt |
| User story | US44: Calculate savings |
| Acceptance criteria | Savings = total income − total actual expenses; works with no budget; expenses exceeding income is treated as debt, not negative savings. |
| Sprint | Sprint 5 |
| Implementation | Backend calculation service, API endpoint, React Native display on the dashboard |
| Testing | Unit test on the calculation, integration test on the endpoint, acceptance test against US44's criteria |
| Increment | A user can see their savings figure on the dashboard at the end of Sprint 5. |

The same chain applies to every backlog item: its epic and sprint are fixed in Section 5, its criteria are in Section 6 (or will be added at refinement per Section 7), and its test coverage is checked against the Definition of Done before the Product Owner accepts it.

# 10. Open Points

A few decisions are already reflected in the Product Vision document but are worth restating here so they are not mistaken for finished work:

- PostgreSQL and the self hosted Jenkins pipeline are the agreed technology choices for Sprint 0; they are planned, and become "done" only once Sprint 0's setup work is actually merged.

- The exact branch/review/merge workflow (Definition of Done, Section 7) is still being finalized by the developers and the Scrum Master.

- The warning threshold for the budget goal notification (US56) needs a specific number agreed with the Product Owner before Sprint 6: the Product Vision document does not fix one.

- If the academic calendar ends up shorter than eighteen weeks, Sprint 7 (AI Assistant) is the sprint to trim first, since the rest of the product stands on its own without it.

# 11. Closing Note

The point of this revision is not to add more content but to make the same product easier to follow: an ordered backlog that shows what gets built before what, acceptance criteria for the stories that most need them now, and a sprint plan a reader can trace back to specific requirements. The Product Vision document remains the source of truth for the financial rules themselves; this document is the build plan for delivering them.